## Sheet1
# | Tasks | Interaction | PIC | Support | Complexity | Start-date | Act_Start-date | End-date | Act_End-date | Duration | Status | Note
Tuần 1 | 11/05/2026 - 17/05/2026
1 | Project Initiation & Topic Confirmation | Iteration 1 | Chương | All | Medium | 2026-05-11 | 2026-05-11 | 2026-05-17 | 2026-05-17 | 7 |  | Milestone: CareBridge topic and initial product direction confirmed
1.1 | Team role assignment | Iteration 1 | Chương | All | Simple | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 1 | Done | Leader and member responsibilities confirmed
1.2 | Define CareBridge initial community-first scope | Iteration 1 | Chương | All | Medium | 2026-05-12 | 2026-05-12 | 2026-05-14 | 2026-05-14 | 3 | Done | CareBridge positioned as maternal and early childhood community support platform
1.3 | Identify stakeholders and target users | Iteration 1 | Phương | Chương | Medium | 2026-05-13 | 2026-05-13 | 2026-05-15 | 2026-05-15 | 3 | Done | Mother, family member, verified expert, moderator, content admin, admin, partner
1.4 | Collect initial references and project materials | Iteration 1 | Bách | All | Medium | 2026-05-14 | 2026-05-14 | 2026-05-17 | 2026-05-17 | 4 | Done | Input for Report 1, Report 2 and early SRS baseline
Tuần 2 | 18/05/2026 - 24/05/2026
2 | Report 1 Preparation | Iteration 1 | All | All | Complex | 2026-05-18 | 2026-05-18 | 2026-05-24 | 2026-05-24 | 7 |  | Deliverable: Report 1 - Project Introduction
2.1 | Write project background and motivation | Iteration 1 | Phương | Chương | Medium | 2026-05-18 | 2026-05-18 | 2026-05-19 | 2026-05-19 | 2 | Done | Maternal and early childhood healthcare support context
2.2 | Write problem statement and user pain points | Iteration 1 | Chương | Huy | Medium | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-20 | 2 | Done | Fragmented care information, misinformation, missed reminders, privacy concerns
2.3 | Write objectives and expected outcomes | Iteration 1 | Chương | Phương | Medium | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2 | Done | Project goals, academic outputs and MVP validation
2.4 | Research related systems and competitors | Iteration 1 | Bách | Lâm | Complex | 2026-05-20 | 2026-05-20 | 2026-05-22 | 2026-05-22 | 3 | Done | Pregnancy tracking, baby care, community and expert support apps
2.5 | Review and finalize Report 1 | Iteration 1 | All | All | Medium | 2026-05-23 | 2026-05-23 | 2026-05-24 | 2026-05-24 | 2 | Done | Report 1 final team review completed
Tuần 3 | 25/05/2026 - 31/05/2026
3 | Report 2 Project Management Plan | Iteration 1 | All | - | Complex | 2026-05-25 | 2026-05-25 | 2026-05-31 | 2026-05-31 | 7 |  | Deliverable: Report 2 - Project Management Plan
3.1 | Define scope and estimation | Iteration 1 | Chương | Huy | Complex | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | 2 | Done | Scope aligned with 14-week plan and MVP feasibility
3.2 | Create WBS and task breakdown | Iteration 1 | Chương | All | Medium | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 2 | Done | Task plan updated from planning, requirement, design, implementation and testing
3.3 | Prepare schedule management plan | Iteration 1 | Huy | Chương | Medium | 2026-05-27 | 2026-05-27 | 2026-05-28 | 2026-05-28 | 2 | Done | Milestones aligned with Report 1-7 deliverables
3.4 | Prepare resource management plan | Iteration 1 | Phương | All | Medium | 2026-05-28 | 2026-05-28 | 2026-05-29 | 2026-05-29 | 2 | Done | Team responsibility allocation
3.5 | Prepare risk management plan | Iteration 1 | Bách | Chương | Complex | 2026-05-29 | 2026-05-29 | 2026-05-30 | 2026-05-30 | 2 | Done | AI safety, healthcare boundary, device limitations and schedule risks
3.6 | Prepare communication and quality plan | Iteration 1 | Lâm | All | Medium | 2026-05-30 | 2026-05-30 | 2026-05-31 | 2026-05-31 | 2 | Done | Meeting, reporting, QA and review approach
Tuần 4 | 01/06/2026 - 07/06/2026
4 | R&D Demo, Requirement Refinement and GitLab Setup | Iteration 1 | All | - | Complex | 2026-06-01 | 2026-06-01 | 2026-06-07 | 2026-06-07 | 7 | Done | Milestone: R&D demo and development infrastructure direction
4.1 | ECG healthcare application research | Iteration 1 | Chương | Phương | Complex | 2026-06-01 | 2026-06-01 | 2026-06-05 | 2026-06-05 | 5 | Done | Research-only feasibility input for innovation discussion
4.2 | IMU sensor application research | Iteration 1 | Phương | Chương | Complex | 2026-06-01 | 2026-06-01 | 2026-06-05 | 2026-06-05 | 5 | Done | Input for MF-21 Smart Activity Monitoring
4.3 | Assess ECG/IMU fit for CareBridge community app | Iteration 1 | Bách | All | Complex | 2026-06-02 | 2026-06-02 | 2026-06-06 | 2026-06-06 | 5 | Done | Decide which innovation items can become MVP or prototype
4.4 | Prepare R&D demo material | Iteration 1 | Lâm | All | Medium | 2026-06-04 | 2026-06-04 | 2026-06-06 | 2026-06-06 | 3 | Done | Demo material for mentor review
4.5 | R&D demo and feedback collection | Iteration 1 | Chương | All | Medium | 2026-06-07 | 2026-06-07 | 2026-06-07 | 2026-06-07 | 1 | Done | Mentor feedback captured for implementation planning
4.6 | Create GitLab repository | Iteration 1 | Huy | Bách | Simple | 2026-06-02 | 2026-06-02 | 2026-06-03 | 2026-06-03 | 2 | Done | Repository prepared for source code and SDLC structure
4.7 | Define Git branch strategy | Iteration 1 | Huy | All | Simple | 2026-06-03 | 2026-06-03 | 2026-06-04 | 2026-06-04 | 2 | Done | main/develop/member feature branches and merge request policy
4.8 | Setup SDLC folder structure | Iteration 1 | Huy | Bách | Medium | 2026-06-04 | 2026-06-04 | 2026-06-07 | 2026-06-07 | 4 | Done | 00 Policy, 01 Planning, 02 Requirement, 03 Design, 04 Implement, 05 Development, 06 Testing, 07 Reports, 08 References
Tuần 5 | 08/06/2026 - 14/06/2026
5 | Report 3 SRS Baseline and Submission Package | Iteration 1 | All | - | Complex | 2026-06-08 | 2026-06-08 | 2026-06-16 | 2026-06-16 | 9 | Done | Milestone: Reports 1, 2 and 3 submission package
5.1 | Report 3 task assignment meeting | Iteration 1 | Chương | All | Simple | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 1 | Done | Assign SRS sections by actor, use case, screen and data responsibility
5.2 | MF21 functional requirement baseline | Iteration 1 | Huy | Chương | Complex | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 3 | Done | Baseline covers 21 major features and community-first business logic
5.3 | Actor and use case model update | Iteration 1 | Phương | Lâm | Complex | 2026-06-09 | 2026-06-09 | 2026-06-12 | 2026-06-12 | 4 | Done | Actor model and 241 use cases prepared for traceability
5.4 | Non-functional requirements specification | Iteration 1 | Lâm | Huy | Medium | 2026-06-09 | 2026-06-09 | 2026-06-11 | 2026-06-11 | 3 | Done | Security, privacy, reliability, performance, portability and maintainability
5.5 | Screen flow and wireframe specification | Iteration 1 | Lâm | Phương | Complex | 2026-06-10 | 2026-06-10 | 2026-06-14 | 2026-06-14 | 5 | Done | Mobile, Expert Portal, Admin Portal and Partner Portal screen descriptions
5.6 | ERD description and data dictionary update | Iteration 1 | Bách | Huy | Complex | 2026-06-10 | 2026-06-10 | 2026-06-14 | 2026-06-14 | 5 | Done | Logical model with 67 entities aligned to UC241
5.7 | SRS review and consistency check | Iteration 1 | Chương | All | Complex | 2026-06-13 | 2026-06-13 | 2026-06-15 | 2026-06-15 | 3 | Done | Check actor, UC, screen, ERD and safety boundary consistency
5.8 | Report 1, Report 2, Report 3 submission | Iteration 1 | Chương | All | Medium | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-16 | 2 | Done | Final deadline 16/06/2026
Tuần 6 | 15/06/2026 - 21/06/2026
6 | System Architecture Design | Iteration 2 | All | - | Complex | 2026-06-15 |  | 2026-06-21 |  | 7 |  | Deliverable: Report 4 architecture baseline and design backlog
6.1 | Update SRS based on supervisor and mentor feedback | Iteration 2 | Chương | All | Medium | 2026-06-15 |  | 2026-06-17 |  | 3 | Done | Freeze requirement baseline before design
6.2 | Create high-level system architecture diagram | Iteration 2 | Huy | Bách | Complex | 2026-06-16 |  | 2026-06-18 |  | 3 | Done | Mobile App, Expert Portal/App, Admin Portal, Partner Portal, Backend, AI, Map, Notification and Realtime services
6.3 | Create technology architecture diagram | Iteration 2 | Huy | Bách | Complex | 2026-06-17 |  | 2026-06-19 |  | 3 | Done | Flutter mobile, backend API, database, storage, map, notification, AI/RAG and realtime service
6.4 | Create software architecture diagram | Iteration 2 | Huy | Chương | Complex | 2026-06-18 |  | 2026-06-20 |  | 3 | Done | Presentation API, business logic, persistence, shared modules, external integrations
6.5 | Write Architecture Decision Records | Iteration 2 | Chương | Huy | Complex | 2026-06-18 |  | 2026-06-21 |  | 4 | Done | ADR for Flutter, backend architecture, database, map service, AI service, notification and IMU boundary
6.6 | Define deployment and environment architecture | Iteration 2 | Bách | Huy | Medium | 2026-06-19 |  | 2026-06-21 |  | 3 | Done | Development, QA/demo and production-like demo environment
6.7 | Review architecture with team and mentor | Iteration 2 | Chương | All | Medium | 2026-06-21 |  | 2026-06-21 |  | 1 | Done | Milestone: Architecture baseline approved for detailed design
Tuần 7 | 22/06/2026 - 28/06/2026
7 | Detailed Design and Source Code Structure | Iteration 2 | All | - | Complex | 2026-06-22 |  | 2026-06-28 |  | 7 |  | Deliverable: Report 4 detailed design package
7.1 | Finalize ERD and physical database schema | Iteration 2 | Phương | Huy | Complex | 2026-06-22 |  | 2026-06-24 |  | 3 | Done | Convert 67-entity logical data model into implementable schema and migrations
7.2 | Design backend source code structure | Iteration 2 | Huy | Bách | Complex | 2026-06-22 |  | 2026-06-25 |  | 4 | Done | Modules, controllers, services, repositories, DTOs, validators, guards and shared utilities
7.3 | Design Flutter mobile source code structure | Iteration 2 | Phương | Lâm | Complex | 2026-06-23 |  | 2026-06-25 |  | 3 | Done | Feature-first structure for mother, family member and expert app flows | Có 1 bộ skill giao diện
7.4 | Design web portal source code structure | Iteration 2 | Lâm | Huy | Complex | 2026-06-23 |  | 2026-06-26 |  | 4 | Done | Admin, content admin, moderator, expert portal and partner portal structure
7.5 | Define API specification and DTO contracts | Iteration 2 | Huy | Bách | Complex | 2026-06-24 |  | 2026-06-27 |  | 4 | To Do | REST endpoints, request/response DTOs, validation, error codes and authorization matrix
7.6 | Define coding convention and review checklist | Iteration 2 | Chương | All | Medium | 2026-06-25 |  | 2026-06-27 |  | 3 | To Do | Naming, package rules, branch rules, commit rules and merge request checklist
7.7 | Setup CI/CD and project skeleton | Iteration 2 | Huy | Bách | Complex | 2026-06-26 |  | 2026-06-28 |  | 3 | To Do | Backend, mobile and web skeletons with build/test pipeline
7.8 | Report 4 design review | Iteration 2 | Chương | All | Medium | 2026-06-28 |  | 2026-06-28 |  | 1 | To Do | Milestone: Detailed design ready for implementation
Tuần 8 | 29/06/2026 - 05/07/2026
8 | Foundation Implementation Package | Iteration 3 | All | - | Complex | 2026-06-29 |  | 2026-07-05 |  | 7 |  | Software Package 1 foundation scope
8.1 | Implement authentication and OTP flow | Iteration 3 | Huy | Lâm | Complex | 2026-06-29 |  | 2026-07-01 |  | 3 | To Do | UC-01 to UC-07 core account flows
8.2 | Implement RBAC and user role management | Iteration 3 | Huy | Bách | Complex | 2026-06-30 |  | 2026-07-02 |  | 3 | To Do | User, mother, family member, expert, moderator, content admin, admin and partner roles
8.3 | Implement account profile and community profile | Iteration 3 | Phương | Lâm | Medium | 2026-06-30 |  | 2026-07-03 |  | 4 | To Do | Profile, community display and privacy-by-default behavior
8.4 | Implement notification foundation | Iteration 3 | Bách | Huy | Complex | 2026-07-01 |  | 2026-07-04 |  | 4 | To Do | Notification preferences, in-app notification, push/mock notification channel
8.5 | Implement audit log foundation | Iteration 3 | Bách | Huy | Medium | 2026-07-02 |  | 2026-07-04 |  | 3 | To Do | Audit important auth, permission and admin actions
8.6 | Implement initial mobile app shell | Iteration 3 | Lâm | Phương | Medium | 2026-07-03 |  | 2026-07-05 |  | 3 | To Do | Welcome, register, login, home shell and navigation
8.7 | Unit and integration tests for foundation modules | Iteration 3 | All | - | Complex | 2026-07-04 |  | 2026-07-05 |  | 2 | To Do | Test cases and defect list for Report 5 update
Tuần 9 | 06/07/2026 - 12/07/2026
9 | Care Journey Core Implementation | Iteration 3 | All | - | Complex | 2026-07-06 |  | 2026-07-12 |  | 7 |  | Software Package 1 core user value scope
9.1 | Implement Mother Care Journey module | Iteration 3 | Phương | Huy | Complex | 2026-07-06 |  | 2026-07-08 |  | 3 | To Do | Mother journey setup, dashboard, stage-based content and maternal metrics
9.2 | Implement Pregnancy Exercise and Posture Support baseline | Iteration 3 | Phương | Lâm | Complex | 2026-07-06 |  | 2026-07-10 |  | 5 | To Do | Exercise list, safety check, session, posture feedback placeholder and history
9.3 | Implement Baby Care Journey module | Iteration 3 | Phương | Bách | Complex | 2026-07-07 |  | 2026-07-10 |  | 4 | To Do | Baby profile, daily log, milestone, growth and vaccination baseline
9.4 | Implement health records and file management | Iteration 3 | Bách | Huy | Complex | 2026-07-08 |  | 2026-07-11 |  | 4 | To Do | Upload, view, delete, source label and permission-aware access
9.5 | Implement reminders, tasks and checklist module | Iteration 3 | Lâm | Phương | Medium | 2026-07-09 |  | 2026-07-11 |  | 3 | To Do | Today tasks, appointment reminders, vaccination reminders and checklist progress
9.6 | Integrate mobile app with backend core APIs | Iteration 3 | All | - | Complex | 2026-07-10 |  | 2026-07-12 |  | 3 | To Do | End-to-end smoke test for foundation and care journey
9.7 | Prepare Software Package 1 evidence | Iteration 3 | Chương | All | Medium | 2026-07-11 |  | 2026-07-12 |  | 2 | To Do | Milestone: Software Package 1 with source code, DB script, tests and updated reports
Tuần 10 | 13/07/2026 - 19/07/2026
10 | Community, Expert and Admin Implementation | Iteration 3 | All | - | Complex | 2026-07-13 |  | 2026-07-19 |  | 7 |  | Software Package 2 main community and expert ecosystem scope
10.1 | Implement Community Q&A module | Iteration 3 | Bách | Lâm | Complex | 2026-07-13 |  | 2026-07-15 |  | 3 | To Do | Community question, answer, anonymous display, bookmark, like and topic follow
10.2 | Implement moderation and report workflow | Iteration 3 | Lâm | Chương | Complex | 2026-07-14 |  | 2026-07-17 |  | 4 | To Do | Moderation queue, report resolution, warning, suspend and content lock
10.3 | Implement verified expert profile and verification workflow | Iteration 3 | Huy | Bách | Complex | 2026-07-14 |  | 2026-07-17 |  | 4 | To Do | Expert profile, credentials upload, verification, renewal and suspension state
10.4 | Implement expert directory, search and filter | Iteration 3 | Phương | Lâm | Medium | 2026-07-15 |  | 2026-07-18 |  | 4 | To Do | Expert list, profile, filter by specialty, availability and rating
10.5 | Implement content and checklist admin module | Iteration 3 | Lâm | Phương | Complex | 2026-07-16 |  | 2026-07-19 |  | 4 | To Do | Content, FAQ, checklist and pregnancy exercise management screens
10.6 | Implement admin dashboard baseline | Iteration 3 | Huy | Chương | Medium | 2026-07-17 |  | 2026-07-19 |  | 3 | To Do | Community, expert, report and operation dashboard baseline
10.7 | Prepare Software Package 2 partial evidence | Iteration 3 | Chương | All | Medium | 2026-07-19 |  | 2026-07-19 |  | 1 | To Do | Package 2 checkpoint: community, expert and admin flows
Tuần 11 | 20/07/2026 - 26/07/2026
11 | Consultation, Family Sync and Monetization Implementation | Iteration 4 | All | - | Complex | 2026-07-20 |  | 2026-07-26 |  | 7 |  | Iteration 4 begins: consultation and integration-heavy features
11.1 | Implement expert availability and consultation pricing | Iteration 4 | Huy | Bách | Complex | 2026-07-20 |  | 2026-07-22 |  | 3 | To Do | Price bands, expert price setup and booking price lock
11.2 | Implement private consultation booking flow | Iteration 4 | Phương | Lâm | Complex | 2026-07-21 |  | 2026-07-24 |  | 4 | To Do | Book expert, select time, select consultation mode and review booking
11.3 | Implement mock payment and commission calculation | Iteration 4 | Bách | Huy | Complex | 2026-07-22 |  | 2026-07-25 |  | 4 | To Do | Payment transaction, commission record, refund/dispute placeholder
11.4 | Implement realtime consultation session baseline | Iteration 4 | Huy | Lâm | Complex | 2026-07-23 |  | 2026-07-26 |  | 4 | To Do | Chat baseline and placeholder for voice/video session through realtime service
11.5 | Implement health summary sharing with expert | Iteration 4 | Phương | Bách | Complex | 2026-07-23 |  | 2026-07-26 |  | 4 | To Do | Generate summary, grant permission, view shared summary and revoke access
11.6 | Implement Family Sync and care group module | Iteration 4 | Lâm | Phương | Complex | 2026-07-24 |  | 2026-07-26 |  | 3 | To Do | Care group, invite family, shared calendar, assigned task and family alert view
11.7 | Integration test for consultation and family flows | Iteration 4 | All | - | Complex | 2026-07-25 |  | 2026-07-26 |  | 2 | To Do | Update defect list and test evidence
Tuần 12 | 27/07/2026 - 02/08/2026
12 | AI, Emergency Map, Device and Smart Safety Implementation | Iteration 4 | All | - | Complex | 2026-07-27 |  | 2026-08-02 |  | 7 |  | Software Package 3 innovation scope and Report 4 submission milestone
12.1 | Implement AI intake and risk triage workflow | Iteration 4 | Phương | Huy | Complex | 2026-07-27 |  | 2026-07-29 |  | 3 | To Do | Green/yellow/red risk routing, safe recommendation and no-diagnosis guardrails
12.2 | Implement Emergency Map and Nearby Care Support | Iteration 4 | Lâm | Huy | Complex | 2026-07-28 |  | 2026-07-31 |  | 4 | To Do | Nearby care facility, route/ETA, quick call and emergency-care disclaimer
12.3 | Implement connected health device mock/import | Iteration 4 | Bách | Phương | Complex | 2026-07-28 |  | 2026-07-31 |  | 4 | To Do | Health device connection, manual/mock import, trend view and source label
12.4 | Implement Smart Activity Monitoring with IMU | Iteration 4 | Chương | Huy | Complex | 2026-07-29 |  | 2026-08-01 |  | 4 | To Do | Safety monitoring settings, suspected fall/impact detection, countdown and false-positive feedback
12.5 | Implement safety alert and family notification flow | Iteration 4 | Huy | Bách | Complex | 2026-07-30 |  | 2026-08-02 |  | 4 | To Do | Safety event, emergency alert, location snapshot and notification service integration
12.6 | Finalize Report 4 Software Design Description | Iteration 4 | Chương | All | Complex | 2026-07-27 |  | 2026-07-28 |  | 2 | To Do | Milestone: Report 4 submission deadline 28/07/2026
12.7 | Prepare Software Package 3 checkpoint | Iteration 4 | All | - | Medium | 2026-08-01 |  | 2026-08-02 |  | 2 | To Do | AI, map, device and IMU features integrated for demo
Tuần 13 | 03/08/2026 - 09/08/2026
13 | Full Integration, Testing and Deployment | Iteration 4 | All | - | Complex | 2026-08-03 |  | 2026-08-09 |  | 7 |  | Deliverable: Full software package and Report 5 test evidence
13.1 | Full system integration and smoke testing | Iteration 4 | All | - | Complex | 2026-08-03 |  | 2026-08-05 |  | 3 | To Do | End-to-end flows across mobile, backend, web portals and external mocks
13.2 | Write and execute unit test cases | Iteration 4 | Huy | Bách | Complex | 2026-08-03 |  | 2026-08-06 |  | 4 | To Do | TDD/UT evidence for backend and selected mobile/web logic
13.3 | Write and execute integration test cases | Iteration 4 | Bách | Huy | Complex | 2026-08-04 |  | 2026-08-07 |  | 4 | To Do | API, database, notification, payment mock, AI mock, map mock and realtime mock
13.4 | Write and execute system test cases | Iteration 4 | Phương | Lâm | Complex | 2026-08-05 |  | 2026-08-08 |  | 4 | To Do | Role-based user scenarios and critical healthcare-safety flows
13.5 | Perform security, privacy and abuse-prevention testing | Iteration 4 | Chương | Huy | Complex | 2026-08-06 |  | 2026-08-08 |  | 3 | To Do | RBAC, consent, audit log, data sharing, report and safety boundary checks
13.6 | Prepare deployment package and database scripts | Iteration 4 | Huy | Bách | Complex | 2026-08-07 |  | 2026-08-09 |  | 3 | To Do | Workable source code, environment guide, database migration and seed data
13.7 | Update Reports 3, 4 and 5 with implementation evidence | Iteration 4 | Chương | All | Complex | 2026-08-08 |  | 2026-08-09 |  | 2 | To Do | Milestone: Full software package ready for final transition
Tuần 14 | 10/08/2026 - 16/08/2026
14 | Final Delivery, User Guide and Defense Preparation | Iteration 4 | Chương | All | Complex | 2026-08-10 |  | 2026-08-16 |  | 7 |  | Deliverable: Reports 6, 7, final product package and defense preparation
14.1 | Final bug fixing and regression testing | Iteration 4 | All | - | Complex | 2026-08-10 |  | 2026-08-12 |  | 3 | To Do | Fix priority defects and verify no critical regression
14.2 | Prepare Report 6 User Guide | Iteration 4 | Phương | Lâm | Complex | 2026-08-10 |  | 2026-08-13 |  | 4 | To Do | Installation guide, mobile user guide, web portal guide and troubleshooting
14.3 | Prepare Report 7 Final Project Report | Iteration 4 | Chương | All | Complex | 2026-08-11 |  | 2026-08-14 |  | 4 | To Do | Final consolidated project document
14.4 | Prepare final source code and database package | Iteration 4 | Huy | Bách | Complex | 2026-08-12 |  | 2026-08-14 |  | 3 | To Do | Source code, database scripts, environment files and release notes
14.5 | Prepare defense presentation slides and demo script | Iteration 4 | Lâm | Chương | Medium | 2026-08-13 |  | 2026-08-15 |  | 3 | To Do | Slides, demo scenario, backup screenshots and Q&A notes
14.6 | Defense rehearsal and member Q&A preparation | Iteration 4 | All | - | Medium | 2026-08-14 |  | 2026-08-16 |  | 3 | To Do | Role-based speaking parts and difficult question practice
14.7 | Final submission | Iteration 4 | Chương | All | Medium | 2026-08-16 |  | 2026-08-16 |  | 1 | To Do | Milestone: final package submitted