CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

CareBridge: A Maternal and Early ChildhoodHealthcare Platform

– Hanoi, May 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	13

1.3 Project Risks	16

2. Management Approach	17

2.1 Project Process	18

2.2 Quality Management	21

2.3 Training Plan	23

3. Project Deliverables	24

4. Responsibility Assignments	25

5. Project Communications	26

6. Configuration Management	27

6.1 Document Management	27

6.2 Source Code Management	27

6.3 Tools & Infrastructures	27

6.4 Task and Workflow Management	28

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 28/05/2026 | A | ChuongBD | Create initial Report 2 draft |
| 28/05/2026 | M | ChuongBD | Update project planning, governance, scalability, and legal sections |
| 30/05/2026 | M | ChuongBD | Update project scope from clinic-centric model to community-based health support model |
| 30/05/2026 | M | ChuongBD | Add AI Safety, Community Governance, Privacy, Consent, and Compliance planning |
| 30/05/2026 | M | ChuongBD | Add Sustainability & Funding Model and Responsibility Matrix considerations |
| 30/05/2026 | M | ChuongBD | Revise WBS estimation and management approach based |
| 13/06/2026 | A | ChuongBD | Add table name |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

#### 1.1.1 Project Overview

CareBridge is a community-based maternal and early childhood health support platform designed to provide a safe, accessible, and trustworthy digital ecosystem for pregnant mothers, postpartum mothers, infants, young children, family members, verified experts, partner organizations, and community operators.

The platform bridges the gap between daily care management, trusted health education, moderated community support, expert connection, AI-assisted risk triage, family coordination, and safety-oriented digital support. CareBridge is designed as a healthcare-support platform, not as a hospital information system, telemedicine provider, or emergency dispatch service.

The MVP is implemented within the SEP490 Capstone Project period to validate the feasibility of the product direction, technical architecture, governance framework, and user engagement model. The project follows a Hanoi-first pilot strategy. Nationwide expansion is considered only after the pilot scope has been validated technically, operationally, and academically.

CareBridge strictly follows healthcare safety boundaries. The system does not diagnose diseases, prescribe medication, provide treatment, replace direct medical examination, or replace emergency services. AI and community functions only support intake, summarization, risk classification, and safe next-action guidance.

#### 1.1.2 Scope Statement

The scope of the CareBridge MVP includes the design, implementation, testing, documentation, and controlled deployment of a digital platform for community-based maternal and early childhood health support. The scope is limited to features that can be implemented within the academic project timeline while still demonstrating the project’s core social-impact value.

The project scope is organized into the following functional domains:

| Domain | Included features | Primary platforms |
| --- | --- | --- |
| Mobile Application | Registration, authentication, profile management, mother journey, baby journey, health records, reminders, Family Sync, AI intake, community participation, safety monitoring, and emergency support entry points. | Flutter Mobile App |
| Community Platform | Anonymous posting, community feed, category management, reporting mechanism, moderation workflow, expert responses, source labels, and community governance. | Mobile App + Backend + Admin Portal |
| Expert Ecosystem | Expert profile, verification workflow, contribution mechanism, consultation request handling, expert responses, availability, and rating/reputation support. | Expert Portal + Mobile App + Backend |
| AI Safety & Risk Triage | Structured intake, symptom normalization, green/yellow/red risk routing, safe recommendation, red-flag detection, disclaimer, logging, and no-diagnosis guardrails. | Mobile App + Backend + AI/Rule Engine |
| Health Data, Consent & Family Coordination | Personal health records, source labeling, temporary sharing, consent scope, family invitation, shared care tasks, care calendar, and audit trail. | Mobile App + Backend |
| Smart Activity Monitoring & Safety Support | Optional IMU-based safety monitoring, suspected fall/impact detection, safety confirmation countdown, family alert, false-positive feedback, safety event history, and emergency support handoff. | Mobile App + Phone IMU + Backend + Notification Service |
| Partner & Nearby Care Support | Partner clinic listing, sponsored service governance, emergency map, nearby care search, quick call, route support, and location sharing with consent. | Partner/Admin Portal + Mobile App + Map Service |
| Administration & Governance Portal | User management, expert verification, moderation dashboard, report processing, governance monitoring, audit log review, partner approval, dashboard, and compliance monitoring. | Admin Portal + Backend |

Table 1. Functional Domain Scope of the CareBridge MVP

The MVP intentionally prioritizes safe and demonstrable functionality over commercial-scale operation. Advanced payment, full video consultation, national infrastructure integration, clinical decision support, and official medical record exchange are not required for the academic MVP.

Figure 1. Core CareBridge workflow and system boundary
Detail: Core CareBridge workflow and system boundary

#### 1.1.3 Scope Assumptions

- Users in the pilot target group have access to smartphones and internet connectivity.

- The project team consists of five active members and follows the official SEP490 timeline.

- The MVP is piloted for Hanoi metropolitan users first; nationwide scaling is not part of MVP validation.

- Verified experts are manually reviewed and approved during the MVP phase.

- Third-party AI or rule-based services remain available during development, or can be replaced with mock/rule-based implementation for demonstration.

- Notification services are available for account, reminder, moderation, and family alert use cases.

- Mobile operating systems continue to provide motion sensor access under user permission and device limitations.

- Map and location services are used only when the user opens emergency/nearby-care support and grants location permission.

- Stakeholders and supervisors provide timely feedback during review sessions.

- The team can use mock data where real integrations would exceed academic project feasibility.

#### 1.1.4 Scope Constraints

| Constraint Type | Description | Project Impact |
| --- | --- | --- |
| Schedule | The project follows a 14-week working plan starting from 11/05/2026, with Reports 1, 2, and 3 due on 16/06/2026 and Report 4 due on 28/07/2026. | The team must prioritize MVP features and avoid overbuilding late-roadmap modules. |
| Resource | The development team consists of five students with academic commitments and limited implementation capacity. | Scope must be decomposed into feasible modules with clear ownership. |
| Budget | The project primarily relies on open-source tools, educational services, mock integrations, and low-cost cloud resources. | Commercial integrations such as full payment gateway or large-scale video calling may be simulated. |
| Healthcare Safety | CareBridge cannot diagnose, treat, prescribe, replace emergency services, or operate as a licensed telemedicine system. | All AI, expert, community, and emergency flows must include disclaimers and safe routing. |
| Data Protection | Health records, pregnancy data, child data, mental health data, consultation records, and location/sensor events are sensitive. | Consent, RBAC, encryption design, audit log, and minimal data sharing are mandatory. |
| Mobile Sensor Limitation | IMU monitoring depends on device hardware, OS permission, battery mode, and foreground/background restrictions. | The feature must be optional, consent-based, and cannot guarantee continuous monitoring on all devices. |

Table 2. CareBridge MVP Scope Constraints

#### 1.1.5 Scope Exclusions

- Official Electronic Medical Record interoperability and national healthcare database integration.

- Electronic prescription, medication dosage recommendation, clinical diagnosis, or treatment planning.

- Licensed telemedicine service positioning, official online medical examination, or emergency dispatch operation.

- Insurance claim processing, hospital resource scheduling, and hospital internal HIS/EMR workflow.

- Medical imaging analysis, clinical decision support systems, and regulated medical-device certification.

- Nationwide deployment infrastructure and commercial-scale operation during the academic MVP.

- Continuous background safety monitoring guarantee across all devices and operating systems.

- Selling, sharing, or using personal health data for advertising or commercial targeting without explicit consent.

#### 1.1.6 Work Breakdown Structure (WBS) & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) | Description |
| --- | --- | --- | --- | --- |
| 1 | Project Initiation & Management |  | 18 | Kick-off, planning, progress tracking, meeting minutes, supervisor communication, task tracking. |
| 1.1 | Project charter, scope baseline and revision control | Medium | 4 | Align team and supervisor on community-first healthcare-support positioning. |
| 1.2 | Schedule, sprint and milestone planning | Medium | 5 | Define 14-week roadmap, sprint plan and internal deadlines. |
| 1.3 | Project monitoring and reporting | Medium | 5 | Weekly tracking, issue log, status updates and risk review. |
| 1.4 | Final review and defense preparation | Medium | 4 | Document refinement, rehearsal and final quality check. |
| 2 | Software Requirement Specification |  | 30 | Actor/use case review, requirements, functional specifications, traceability with latest use case baseline. |
| 2.1 | Actor and stakeholder analysis | Medium | 4 | Validate 14-actor structure and platform responsibilities. |
| 2.2 | Use case analysis and diagram preparation | High | 8 | Maintain updated use case list including safety monitoring additions. |
| 2.3 | Functional specification writing | High | 10 | Detailed flows, business rules, exceptions, healthcare safety boundary. |
| 2.4 | Non-functional requirements and appendix | Medium | 4 | Security, performance, usability, reliability, messages and business rules. |
| 2.5 | SRS review and consistency check | Medium | 4 | Ensure Report 2, Report 3, task plan and business logic are consistent. |
| 3 | Authentication, Access Control & Profile |  | 24 | Account, OTP, profile, RBAC, expert status, privacy defaults. |
| 3.1 | Registration, OTP and login/logout | Low | 6 | Account creation and session handling. |
| 3.2 | Profile management and onboarding | Low | 5 | Role-based onboarding for mother, caregiver, expert and partner. |
| 3.3 | Role-based access control | Medium | 6 | User, expert, moderator, admin and partner permissions. |
| 3.4 | Consent and privacy settings | High | 7 | Consent scope, data sharing, revoke and audit hooks. |
| 4 | Mother & Baby Care Journey |  | 38 | Mother journey, baby profile, growth, vaccination, health record and reminders. |
| 4.1 | Mother journey tracking | Medium | 8 | Pre-pregnancy, pregnancy and postpartum dashboard. |
| 4.2 | Baby profile and daily log | Medium | 7 | Breastfeeding, sleep, diaper, fever, notes and night mode. |
| 4.3 | Growth, milestone and vaccination tracking | High | 8 | Charts, records, reminders and source labels. |
| 4.4 | Personal health record vault | Medium | 7 | Upload, tag, categorize and share health records. |
| 4.5 | Reminder and care task engine | Medium | 8 | Appointment, vaccination, vitamin, checklist and daily task reminders. |
| 5 | Community & Knowledge Hub |  | 34 | Community Q&A, anonymous posting, content hub, checklist and moderation support. |
| 5.1 | Community feed and topic management | Medium | 6 | Create, browse, filter and categorize community content. |
| 5.2 | Anonymous posting and privacy prompts | Medium | 5 | Safe asking for sensitive topics while keeping internal traceability. |
| 5.3 | Answer, interaction and source labeling | Medium | 6 | Personal-experience labels and expert-response labels. |
| 5.4 | Report mechanism and moderation queue | High | 9 | Report, triage, hide, lock, warn and escalation. |
| 5.5 | Verified content, FAQ and checklist hub | Medium | 8 | Short-stage content, FAQ and checklist templates. |
| 6 | Verified Expert Ecosystem |  | 30 | Expert verification, contribution, consultation request and reputation. |
| 6.1 | Expert profile and credential submission | Medium | 6 | Specialty, documents, scope and status. |
| 6.2 | Admin verification workflow | High | 7 | Approve, reject, request supplement and log decisions. |
| 6.3 | Expert answer and contribution queue | Medium | 6 | Free expert response within safety boundary. |
| 6.4 | Consultation request and temporary data sharing | High | 7 | Booking request, scope disclaimer and time-limited access. |
| 6.5 | Rating/reputation and complaint handling | Medium | 4 | Verified review and dispute evidence. |
| 7 | AI Risk Triage & Safety Engine |  | 34 | Structured intake, red-flag rule, green/yellow/red routing and safe recommendation. |
| 7.1 | AI intake interface | Medium | 6 | Step-by-step intake for user concern. |
| 7.2 | Structured data normalization | Medium | 5 | Symptom, duration, severity and related profile fields. |
| 7.3 | Risk classification rule engine | High | 8 | Green/yellow/red rules and conservative fallback. |
| 7.4 | Safe recommendation and emergency override | High | 7 | No diagnosis, no prescription, no paid consultation before red-flag routing. |
| 7.5 | AI logging and policy monitoring | Medium | 5 | Prompt/response metadata, report and review. |
| 7.6 | AI safety testing | High | 3 | Medication, emergency, postpartum mental health and child fever scenarios. |
| 8 | Family Sync & Cooperative Care |  | 22 | Care group, shared calendar, task assignment and family alert permissions. |
| 8.1 | Care group invitation | Medium | 5 | Invite by link/phone, account validation and default minimal permissions. |
| 8.2 | Family permission management | High | 6 | Granular sharing for calendar, baby log, alerts and records. |
| 8.3 | Shared calendar and task assignment | Medium | 6 | Care events, responsibility, status and reminders. |
| 8.4 | Family notifications and alert settings | Medium | 5 | Shared reminders and important alerts based on consent. |
| 9 | Smart Activity Monitoring & Safety Support |  | 28 | Optional phone IMU monitoring, suspected fall/impact event, confirmation and family alert. |
| 9.1 | Safety monitoring configuration and consent | Medium | 5 | Explain limits, sensor permission, notification, location optional and contact selection. |
| 9.2 | IMU data processing and on-device feature extraction | High | 6 | Accelerometer/gyroscope sampling, filtering and activity windows. |
| 9.3 | Suspected fall/impact rule detection | High | 6 | Rule/confidence, false-positive prevention and event creation. |
| 9.4 | Safety confirmation countdown | Medium | 4 | Full-screen prompt, vibration/sound and response options. |
| 9.5 | Family alert and notification delivery | High | 4 | Minimal payload, consent and delivery state. |
| 9.6 | Safety history and false-positive feedback | Medium | 3 | Event history, label and anonymized rule improvement. |
| 10 | Emergency Map & Partner/Nearby Care Support |  | 22 | Emergency entry, map, route, quick call, location sharing and partner service listing. |
| 10.1 | Emergency support screen and red-flag routing | High | 5 | Emergency flow and visible disclaimer. |
| 10.2 | Map service and nearby care search | Medium | 5 | Location permission, facility list and route support. |
| 10.3 | Partner profile and service listing | Medium | 5 | Approved partner clinic/service data and sponsored labels. |
| 10.4 | Partner content moderation and referral request | Medium | 4 | Approval, labeling and no data sharing without consent. |
| 10.5 | Location/privacy event logging | Medium | 3 | Minimal metadata and audit trail. |
| 11 | Administration, Governance & Operation Dashboard |  | 30 | User, expert, moderation, partner, audit, impact and compliance dashboards. |
| 11.1 | User and role management | Medium | 5 | View status, lock, unlock and support actions. |
| 11.2 | Expert and partner approval dashboard | High | 6 | Verification, status and audit trail. |
| 11.3 | Moderation dashboard | High | 7 | Queue, report, warning, hide, lock and escalation. |
| 11.4 | Governance and audit dashboard | High | 6 | Access log, consent log, AI/safety log and incident review. |
| 11.5 | Impact and KPI dashboard | Medium | 6 | Community, expert, safety and social-impact statistics. |
| 12 | Infrastructure, DevOps & Quality Assurance |  | 54 | Cloud setup, database, CI/CD, security, testing and final deployment package. |
| 12.1 | Backend infrastructure and database setup | Medium | 8 | Spring Boot services, PostgreSQL/MongoDB and data storage design. |
| 12.2 | Flutter mobile app foundation | High | 8 | Navigation, state management, auth and design system. |
| 12.3 | CI/CD and repository workflow | Medium | 6 | Git workflow, pull request review, build validation. |
| 12.4 | Security, backup and logging setup | High | 7 | Encryption design, backup policy, access log and monitoring. |
| 12.5 | Unit and integration testing | High | 8 | Backend, mobile and API validation. |
| 12.6 | System, performance and security testing | High | 9 | Critical-flow, load, privacy, RBAC and AI safety testing. |
| 12.7 | UAT, defect closure and final package | High | 8 | Representative scenarios, evidence and final release checklist. |
| Total Estimated Effort (man-days) |  |  | 364 |  |

Table 3. Work Breakdown Structure

The rebuilt WBS maps project work to the current approved CareBridge product scope and adds missing planning items for Smart Activity Monitoring, Emergency Support, governance, and safety-risk controls. The estimation uses man-days and is intended for academic planning, not commercial quotation.The figure is intentionally higher than the previous draft because it adds omitted planning work for safety monitoring, emergency support, governance, partner support, AI safety testing, and quality assurance. The project team uses this estimation for workload distribution and prioritization; implementation may use mock integrations where full external integration exceeds academic feasibility.

#### 1.1.7 Geographic Scope

The MVP pilot is limited to the Hanoi metropolitan area. This scope reflects the project’s Hanoi-first strategy, where community growth, expert participation, partner mapping, user feedback, and operational governance can be validated in a controlled environment. Nationwide expansion is treated as a future roadmap after successful pilot validation.

#### 1.1.8 MVP Boundary

| MVP Validation Area | What the MVP must prove | Not intended to prove |
| --- | --- | --- |
| User adoption | Users can register, create profiles, track mother/baby journeys, post questions and use reminders. | Nationwide market acquisition or commercial retention at scale. |
| Community engagement | Users can ask, answer, report and receive moderated support safely. | Unmoderated social-network scale behavior. |
| Expert participation | Verified experts can be reviewed, approved and contributed safely. | Full regulated medical consultation operation. |
| AI safety | Structured intake and green/yellow/red routing can support safe next actions. | AI diagnosis, treatment, prescription or clinical decision support. |
| Family coordination | Care groups, shared tasks, and alerts can reduce caregiver burden. | Full family medical management or legal guardian verification at national level. |
| Safety monitoring | Phone IMU can demonstrate suspected event detection, safety confirmation and consent-based family alert. | Certified medical device behavior, guaranteed fall detection, or emergency dispatch. |
| Partner and emergency support | Map/partner support can guide users toward nearby care and transparent O2O referral. | Guaranteed appointment, ambulance dispatch or priority commercial routing in emergencies. |

Table 4. MVP Validation Boundary

### 1.2 Project Objectives

#### 1.2.1 Overall Objective

The primary objective of CareBridge is to deliver a secure, scalable, and healthcare-safe MVP that supports maternal and early childhood care journeys through education, moderated community participation, verified expert engagement, responsible AI triage, family collaboration, and safety-oriented support flows.

#### 1.2.2 Business Objectives

- Improve access to trusted and actionable maternal and child-care information.

- Reduce misinformation and unsafe peer advice through moderation and expert verification.

- Promote preventive care behavior through reminders, checklist, health records and care tasks.

- Create a community-first product where users can receive support without being forced into paid consultation from the beginning.

- Enable verified experts to build reputation and provide safe educational guidance.

- Validate the Hanoi pilot model before any nationwide expansion.

- Establish a sustainable social-impact direction through optional expert marketplace, partner support, and CSR opportunities without selling personal health data.

#### 1.2.3 Technical Objectives

- Implement Flutter mobile application for the user-facing MVP.

- Implement modular backend services using Java Spring Boot with PostgreSQL and MongoDB where appropriate.

- Apply role-based access control, consent-driven data sharing, and audit logging for sensitive actions.

- Support structured AI/rule-based triage without allowing diagnosis or prescription behavior.

- Support notification flows for reminders, moderation updates, consultation requests, and family safety alerts.

- Support map/location integration only within consent-based emergency or nearby-care flows.

- Design IMU safety monitoring as optional, on-device-first, privacy-aware functionality.

- Maintain cloud-ready architecture and CI/CD workflow for academic deployment and demonstration.

#### 1.2.4 Quality Objectives

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Requirement and Design Review | 100% key documents reviewed | All critical inconsistencies resolved | N/A | Scope, actor, use case, WBS, risk and deliverable consistency. |
| 2 | Unit Testing | >= 80% backend service coverage; >= 90% critical business-rule coverage | <= 10 | <= 10% | Focus on auth, RBAC, triage rule, permission and reminder logic. |
| 3 | Integration Testing | >= 75% key API/service integration coverage | <= 8 | <= 15% | Mobile-backend, AI/rule engine, notification, map and admin flows. |
| 4 | System Testing | 100% critical MVP flows; >= 90% major flows | <= 5 | <= 5% | Includes red-flag flow, moderation, data sharing and safety monitoring. |
| 5 | Security & Privacy Testing | 100% RBAC, consent and sensitive-data access checks | 0 critical defects | 0% | Focus on health records, child data, consultation and safety event logs. |
| 6 | AI Safety Testing | 100% high-risk prompt set executed | 0 Unsafe Responses | 0% | Medication, red flag, child fever, postpartum mental health, self-harm and emergency scenarios. |
| 7 | UAT | 100% MVP scenarios validated | 0 Blocker Defects | 0% | Representative care seeker, family, expert, moderator and admin scenarios. |

Table 5. Quality Objectives and Defect Targets

#### 1.2.5 Schedule Objectives

The project follows a 14-week working plan starting from 11/05/2026. Reports 1, 2, and 3 are aligned for 16/06/2026, Report 4 is aligned for 28/07/2026, and Reports 5, 6, and 7 are prepared before the final defense according to SEP490 scheduling. The team targets a milestone timeliness rate of at least 90% and keeps a final review buffer before defense.

| Activity | Estimated Effort (%) | Management Focus |
| --- | --- | --- |
| Requirement Analysis | 15% | Actor, use case, business rule, risk boundary and SRS alignment. |
| Architecture & Design | 15% | System architecture, ERD, API design, screen flow and security design. |
| Development | 40% | Flutter mobile app, backend services, admin/expert/partner flows, AI/rule services and safety monitoring demo. |
| Testing & QA | 20% | Unit, integration, system, UAT, security, privacy and AI safety testing. |
| Project Management | 10% | Planning, tracking, risk management, communication, configuration and final packaging. |

Table 6. Effort Distribution by Activity Group

#### 1.2.6 Pilot Success Metrics

| Metric | Target for Academic Pilot | Rationale |
| --- | --- | --- |
| MVP critical-flow completion | >= 90% | Most essential flows must be demonstrable by defense. |
| Critical defect count before final package | 0 | No blocker in auth, health record, triage, moderation, consent or emergency/safety flow. |
| User scenario acceptance | >= 90% | Representative user scenarios should pass UAT. |
| AI safety violation rate in test set | 0 critical violations | No diagnosis, prescription, dosage or emergency-delay behavior. |
| Moderation handling coverage | 100% high-risk content scenarios | Medication, red flag, misinformation and abuse reports must be handled. |
| Safety monitoring demo readiness | >= 1 working demo flow | Enable monitoring, detect simulated suspected events, confirm status, alert or emergency handoff. |
| Documentation completion | 100% required SEP490 reports and evidence | Reports, tracking, design, test cases, user guide and final presentation. |

Table 7. Academic Pilot Success Metrics

### 1.3 Project Risks

The risk register is rebuilt to reflect the current CareBridge scope, including healthcare legal boundaries, community governance, AI safety, privacy, location, partner content, and phone-sensor safety monitoring.

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Healthcare legal misunderstanding | High | Medium | Use legal-safe wording: support, guidance, risk triage; never diagnosis, prescription, treatment or emergency replacement. |
| 2 | Unsafe AI recommendation | High | Medium | Restrict AI to structured intake, summarization and safe next-action routing; maintain red-flag override and test prompt set. |
| 3 | Community misinformation | High | High | Apply moderation queue, report button, expert labels, banned keywords and health-risk classifier. |
| 4 | Expert verification failure | High | Medium | Manual review, credential status, badge control, complaint handling and periodic re-check. |
| 5 | Sensitive data leakage | High | Medium | RBAC, consent scope, encryption design, audit log, limited internal access and incident response plan. |
| 6 | Child data privacy risk | High | Medium | Guardian-controlled profiles, privacy prompts, default private settings and no public child identity exposure. |
| 7 | Timeline pressure | High | High | Use sprint prioritization, internal buffers, MVP cuts and weekly risk review. |
| 8 | Cloud deployment complexity | Medium | Medium | Deploy staging early, use simple architecture, document rollback and maintain local fallback demo. |
| 9 | Team lacks scalable architecture experience | Medium | Medium | Conduct training, architecture review, code review and supervisor feedback. |
| 10 | False positive safety detection | Medium | High | Use confirmation countdown, false-positive feedback, on-device filtering and clear “suspected event” wording. |
| 11 | False negative safety detection | High | Medium | Do not claim guaranteed fall detection; include disclaimer and allow manual emergency support. |
| 12 | Battery drain from sensor monitoring | Medium | Medium | Make monitoring optional, display battery notice, optimize sampling and allow scheduled monitoring. |
| 13 | Mobile OS sensor/background limitation | Medium | High | State actual monitoring limitation, test on target device, avoid guaranteeing continuous background operation. |
| 14 | Family alert delivery failure | High | Medium | Track delivery status, retry policy, fallback quick call and minimal payload. |
| 15 | GPS/map unavailable in emergency flow | High | Medium | Allow manual hotline/area search and show no-location fallback. |
| 16 | Partner/sponsored content misleads users | High | Medium | Require admin approval, sponsored label, no ads in AI triage/red-alert recommendation and report workflow. |
| 17 | Payment or paid consultation misconception | Medium | Medium | Use mock/controlled payment; show scope, price, refund policy and no medical guarantee. |
| 18 | Scope creep from too many features | High | High | Separate MVP, should-have and roadmap; prioritize demonstration-critical features. |

Table 8. Project Risk Register

## 2. Management Approach

The CareBridge project adopts Agile Scrum as the primary development methodology because the project involves evolving requirements, user-safety validation, iterative UI/UX refinement, and continuous supervisor feedback. Scrum enables the team to deliver incremental project outcomes through short development cycles while maintaining flexibility in requirement management. In parallel, project monitoring and governance activities are conducted throughout the project lifecycle to continuously track scope, schedule, risks, quality objectives, and deliverable completion against the approved project baseline.

Figure 2. Project Management Framework Applied in CareBridge 
Detail Project Management Framework Applied in CareBridge

### 2.1 Project Process

#### 2.1.1 Development Methodology

The project is implemented with iterative Scrum cycles. Each sprint produces a reviewed increment or deliverable evidence such as requirement update, prototype, API module, test evidence, or document section. Safety, legal boundary, privacy and AI-governance requirements are treated as cross-cutting acceptance criteria for every relevant sprint.

Figure 3. Scrum process model applied in CareBridge
Detail Scrum process model applied in CareBridge

#### 2.1.2 Scrum Roles

| Role | Responsibility |
| --- | --- |
| Product Owner | Prioritize business requirements, MVP boundary, safety scope and deliverable readiness. |
| Scrum Master | Facilitate sprint events, remove blockers, maintain sprint discipline and update progress. |
| Development Team | Analyze, design, implement, test and document the system modules. |
| QA / Reviewer | Review requirements, test cases, defect logs, privacy scenarios, AI safety and UAT evidence. |
| Supervisor/Mentor | Review project outputs, provide guidance and validate academic direction. |

Table 9. Scrum Roles and Responsibilities

#### 2.1.3 Scrum Artifacts

- Product Backlog

- Sprint Backlog

- Sprint Goal

- Increment

- Sprint Burndown/Progress Tracking

- Defect Log

- Risk Register

- Requirement Traceability Matrix

- Change Log

- Meeting Minutes

#### 2.1.4 Sprint Structure

- Sprint Planning

- Requirement Clarification

- Design and UI/API Planning

- Implementation

- Unit Testing

- Integration Testing

- Review and Demonstration

- Retrospective and Backlog Update

#### 2.1.5   14-Week Project Roadmap

| Week | Period | Main Focus | Expected Output |
| --- | --- | --- | --- |
| 1 | 11/05 - 17/05 | Project initiation, problem framing, stakeholder identification, initial product positioning. | Report 1 outline, project direction, meeting minutes. |
| 2 | 18/05 - 24/05 | Report 1 preparation, market/problem analysis, related systems and expected outcomes. | Report 1 completed draft. |
| 3 | 25/05 - 31/05 | Report 2 project management planning, scope, WBS, risk and communication plan. | Report 2 initial draft. |
| 4 | 01/06 - 07/06 | Business logic update, actor/use case redesign, safety boundary confirmation, IMU research demo preparation. | Updated business scope, use case baseline and research demo. |
| 5 | 08/06 - 16/06 | Finalize Reports 1, 2, 3; SRS completion, use case descriptions, non-functional requirements. | Reports 1, 2, 3 submitted by 16/06/2026. |
| 6 | 17/06 - 23/06 | Architecture design, screen flow, ERD, API design, technology proof of concept. | Report 4 design skeleton and prototype evidence. |
| 7 | 24/06 - 30/06 | Core backend and Flutter foundation: auth, profile, mother/baby journey. | Core app framework and backend services. |
| 8 | 01/07 - 07/07 | Community, moderation, content hub and health record implementation. | Community and record modules. |
| 9 | 08/07 - 14/07 | Expert ecosystem, Family Sync, reminders and notification flows. | Expert and family coordination modules. |
| 10 | 15/07 - 21/07 | AI/rule triage, red/yellow/green routing, governance and audit log. | AI safety and governance increment. |
| 11 | 22/07 - 28/07 | Safety monitoring demo, emergency map support, Report 4 finalization. | Report 4 due 28/07/2026; safety demo evidence. |
| 12 | 29/07 - 04/08 | Integration testing, system testing, defect fixing, performance/security validation. | Test evidence and defect log. |
| 13 | 05/08 - 11/08 | User guide, deployment guide, UAT, final software package and documentation consolidation. | Reports 5 and 6 drafts, MVP package. |
| 14 | 12/08 - Final Defense | Final report consolidation, presentation, rehearsal, Q&A preparation and final package verification. | Reports 5, 6, 7 before defense 3 days; final presentation. |

Table 10. Fourteen-Week Project Roadmap

#### 2.1.6 Definition of Done

- Requirement is linked to actor/use case or approved business rule.

- UI/API behavior is documented and reviewed by at least one team member.

- Implementation is committed to the repository with meaningful branch/commit history.

- Unit or integration test evidence is available for implemented logic where applicable.

- No critical or high-severity defect remains open for the completed scope.

- Healthcare safety boundary is checked: no diagnosis, no prescription, no treatment, no emergency replacement.

- Sensitive data access follows RBAC, consent and audit-log expectations.

- Documentation and screenshots/evidence are updated for the sprint increment.

#### 2.1.7 Change Management

Any major requirement change must be reviewed against impact on scope, schedule, WBS, risk, data privacy, healthcare safety and deliverables. Changes that introduce new healthcare-sensitive behavior must be approved only when the team can define safe wording, consent, logging and moderation controls. The project team records major changes in the Record of Changes and updates related report sections to avoid inconsistency.

### 2.2 Quality Management

#### 2.2.1 Quality Management Objectives
Quality management ensures that CareBridge satisfies functional requirements, non-functional requirements, healthcare-safety constraints, data-protection expectations and stakeholder acceptance criteria. Quality assurance is embedded throughout requirements, design, implementation, testing and documentation.

#### 2.2.2 Defect Prevention

- Requirement review sessions

- Design walkthroughs

- Coding standards enforcement

- Architecture review

- Peer review and Merge Request review

- Static analysis and linting

- CI/CD validation

- AI safety prompt testing

- Security and consent scenario review

- Pre-defense document consistency audit

#### 2.2.3 Review Process

| Deliverable | Reviewer | Review Focus |
| --- | --- | --- |
| Project Plan | Team Lead, Supervisor | Scope, schedule, risks, WBS, responsibility and consistency with current business scope. |
| SRS | Development Team, Supervisor | Actors, use cases, functional details, NFR, safety boundary and traceability. |
| Software Design | Development Team | Architecture, screen flow, ERD, APIs, security and deployment feasibility. |
| Source Code | Peer Developers | Code quality, testability, security and maintainability. |
| Test Cases | QA Members | Coverage of critical flows, abnormal cases, AI safety and data privacy. |
| User Guides | Team Lead, QA | Install steps, user flows, screenshots and clarity. |
| Final Package | Entire Team | Build readiness, documentation, evidence and presentation consistency. |

Table 11. Deliverable Review Matrix

#### 2.2.4 Testing Strategy

| Testing Type | Scope | Acceptance Criteria |
| --- | --- | --- |
| Unit Testing | Backend services, rules, validators, permission checks, reminder logic, sensor-event rules. | Core business logic >= 90% where feasible; no critical failed test. |
| Integration Testing | Mobile-backend, admin-backend, notification, AI/rule engine, map and database flow. | Critical integration path passes; retry/failure handling verified. |
| System Testing | End-to-end flows across user, family, expert, moderator, admin and partner paths. | All critical MVP flows pass. |
| Security & Privacy Testing | RBAC, consent, temporary access, audit log, child data and health record sharing. | No unauthorized sensitive data access. |
| AI Safety Testing | Medication, dosage, red flag, diagnosis, self-harm, postpartum mental health and emergency scenarios. | AI never diagnoses, prescribes or delays emergency routing. |
| Sensor Safety Testing | Enable/disable monitoring, suspected event, safety confirmation, family alert, false-positive feedback. | Event wording remains “suspected”; user confirmation is required unless there is no response. |
| UAT | Representative scenarios with care seeker, family member, expert, moderator and admin. | User acceptance rate >= 90%; no critical blocker. |

Table 12. Testing Strategy and Acceptance Criteria

#### 2.2.5 User Acceptance Testing

UAT is conducted using representative scenarios: a mother creates a journey, records baby care data, asks a community question, receives moderated guidance, shares a summary with a verified expert, configures family access, receives reminders, and tests safety monitoring flow. The UAT also covers abnormal cases such as unsafe community advice, red-flag triage, permission revocation, and failed notification delivery.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Flutter Mobile Development | Mobile Team | Week 2-4 / 3 days initial + practice | Mandatory for mobile app implementation. |
| Java Spring Boot Backend | Backend Team | Week 2-4 / 3 days initial + practice | Mandatory for backend implementation. |
| Database Design: PostgreSQL & MongoDB | Backend Team | Week 4-6 / 2 days | Mandatory for data model and persistence. |
| GitLab Workflow and Merge Request Review | Entire Team | Week 1 / 1 day | Mandatory for source control discipline. |
| Cloud Deployment Basics | Entire Team | Week 3-6 / 2 days | Mandatory for demo deployment. |
| AI Safety & Rule-Based Triage | BA, Backend, QA | Week 4-8 / 2 days | Mandatory for AI/risk module. |
| Healthcare Legal Boundary & Privacy | Entire Team | Week 4 / 1 day + review | Mandatory before implementing health-sensitive features. |
| IMU Sensor Prototype and Motion Event Testing | Mobile Team, QA | Week 4-10 / 2 days + demo testing | Mandatory for safety monitoring prototype. |
| Testing, Defect Management and UAT Evidence | QA + Development Team | Week 10-13 / 2 days | Mandatory for Reports 5 and final package. |

Table 13. Project Training Plan

## 3. Project Deliverables

| # | Deliverable | Due Date / Target | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 - Project Introduction | 16/06/2026 | Project background, problem statement, related systems, objectives and expected outcomes. |
| 2 | Report 2 - Project Management Plan | 16/06/2026 | Current document: scope, WBS, risks, process, quality, training, deliverables, RACI, communication and configuration management. |
| 3 | Report 3 - Software Requirement Specification | 16/06/2026 | Actors, use cases, functional specifications, NFR, business rules and appendix. |
| 4 | Research / Prototype Demo Evidence | June 2026 | System design |
| 5 | Report 4 - Software Design Specification | 28/07/2026 | Core features |
| 6 | Software Package Iteration 1 | Early July 2026 | Authentication, profile, mother/baby journey, health records and basic reminders. |
| 7 | Software Package Iteration 2 | Mid July 2026 | Community, moderation, expert profile, Family Sync and notification. |
| 8 | Software Package Iteration 3 | Late July 2026 | AI/rule triage, governance dashboard, emergency support and safety monitoring prototype. |
| 9 | Final Software Package | Before Defense | Integrated MVP, deployment evidence, source code, release notes and demo scenario. |
| 10 | Report 5 - Testing Report | Before Defense | Test plan, test cases, test results, defect log and evidence. |
| 11 | Report 6 - User Guide | Before Defense | Installation guide, user manual and screenshots. |
| 12 | Report 7 - Final Project Report | Before Defense | Consolidated final report following the school template. |
| 13 | Final Presentation and Defense Materials | According to SEP490 schedule | Slides, demo script, Q&A preparation and backup evidence. |

Table 14. Project Deliverables and Milestones

## 4. Responsibility Assignments

Figure 4. Responsibility Structure

Detail Responsibility Structure

The responsibility assignment matrix uses D = Do, R = Review, S = Support, I = Informed. The matrix combines document ownership and technical module responsibility to improve traceability during defense.

| Responsibility | ChuongBD | HuyND | BachNQ | PhuongNT | LamVH |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | D | R | R | S |
| Report 1 - Project Introduction | D | S | D | R | R |
| Report 2 - Project Management Plan | D | S | R | R | S |
| Report 3 - SRS Overview & User Requirements | D | D | S | R | S |
| Report 3 - Functional Specifications | R | D | S | D | R |
| Report 4 - Software Design | D | R | S | I | S |
| Flutter Mobile App Foundation | D | D | I | S | R |
| Backend Development | R | D | I | I | S |
| Database & API Design | R | D | S | I | S |
| Community & Moderation Module | D | S | R | R | S |
| Expert Ecosystem Module | R | D | S | S | R |
| AI Risk Triage & Safety Rules | D | R | S | R | S |
| Smart Activity Monitoring Prototype | D | D | I | S | R |
| Emergency Map & Notification Flow | R | D | S | S | R |
| Testing & QA | R | S | I | D | S |
| Documentation & Formatting | R | I | D | S | D |
| Final Presentation & Demo Script | D | S | R | R | D |

Table 15. Responsibility Assignment Matrix (RAM)

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily Standup | Entire Team | Progress tracking, blockers and short-term tasks. | Daily or working-day basis | Discord, Messenger |
| Sprint Planning | Entire Team | Confirm sprint goal, assign backlog and define acceptance criteria. | Every sprint | Discord, Google meet |
| Sprint Review | Entire Team + Supervisor | Demonstrate increment and collect feedback. | End of sprint / milestone | GitLab + Google meet |
| Technical Review | Development Team | Review architecture, API, code, database and deployment decisions. | Weekly | GitLab + Discord + design docs |
| Requirement Review | Team + Supervisor | Confirm scope, use cases, safety boundary and report consistency. | Before report submission / major change | Google Docs + meeting notes |
| Risk Review | Team Lead + Module Owners | Update risk status and mitigation actions. | Weekly | Discord |
| Supervisor Meeting | Team + Supervisor | Receive academic feedback and align deliverables. | Weekly or scheduled | Google Meet |
| Progress Tracking | Team Lead | Monitor tasks, status, deadlines and blockers. | Weekly | GitLab |
| Defect Triage | QA + Developers | Prioritize defects and assign fixes. | During testing weeks | Issue tracker + test report |
| Final Defense Preparation | Entire Team | Rehearse presentation, demo and Q&A. | Final buffer period | Slides + demo script + dry run |

Table 16. Project Communication Plan

## 6. Configuration Management

### 6.1 Document Management

All project documents are maintained in centralized shared storage. Each report must include version history, change description, owner, and review status. Final submission versions are exported as PDF/DOCX and preserved separately from draft versions. Major updates to scope, use cases, WBS, risk register, timeline, or technology stack must be reflected across related reports to avoid inconsistency.

### 6.2 Source Code Management

Source code is managed through GitLab repositories using a Git-based version control workflow. Feature branches are created for implementation activities and merged through Merge Requests after peer review. Commit messages should be meaningful and linked to task IDs, sprint items, or project deliverables. The main branch must remain stable and demonstrable throughout the project lifecycle. The team maintains README documentation, environment configuration guides, deployment notes, and release records within GitLab to support final package verification and defense preparation.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure | Usage |
| --- | --- | --- |
| Mobile Technology | Flutter | Primary mobile application for care seekers, family members and community users. |
| Backend Technology | Java Spring Boot | Backend APIs, business services, RBAC, consent, triage and governance logic, Spring Security. |
| Database | PostgreSQL, MongoDB | Structured relational data and flexible document/log/content data as needed. |
| Caching / Performance | Redis or lightweight caching strategy | Community feed, FAQ, checklist and read-heavy data optimization when implemented. |
| Notification | Firebase Cloud Messaging or equivalent | Reminders, family alerts, moderation results and consultation updates. |
| Map / Location | TrackAsia link/API or mock nearby-care dataset | Emergency map, nearby care search and routing support in Vietnam. |
| Sensor Prototype | Phone accelerometer/gyroscope | Smart activity monitoring and suspected fall/impact detection demo. |
| IDEs / Editors | Visual Studio Code, IntelliJ IDEA, Android Studio | Development and debugging. |
| Diagramming | DrawIO, PlantUML, Mermaid | Use case, process, architecture, ERD and flow diagrams. |
| Documentation | Microsoft Office, Google Docs/Sheets/Slides | Reports, schedules, meeting notes, slides and shared documents. |
| Version Control | GitLab | Source code management, Merge Requests, issue tracking, repository management, CI/CD pipelines and release packaging. |
| Deployment | GitLab CI/CD, AWS, Vercel | Build automation, deployment, MVP hosting, and demonstration environment management. |
| Project Management | GitLab Boards, Google Sheets | Task planning, sprint tracking, issue management and progress reporting. |

Table 17. Development Tools and Infrastructure

### 6.4 Task and Workflow Management

| Status | Description | Exit Criteria |
| --- | --- | --- |
| To Do | Task identified but not started. | The task has owner, scope and expected output. |
| In Progress | Task currently being implemented or written. | The work item is actively updated and not blocked. |
| Blocked | Waiting for dependency, decision, access, technical issue or review. | Blocker is documented with the owner and next action. |
| Testing | Implementation completed and under testing/review. | Test cases are executed and results recorded. |
| Review | Awaiting peer/supervisor/module-owner validation. | Reviewer confirms acceptance or requests rework. |
| Done | Task successfully completed and evidence stored. | Output is linked to report, code, screenshot, test result or demo evidence. |

Table 18. Task Workflow Status Definition